## Slide 1: ‘First Contact Practitioners’ Implementation of MSK physiotherapy FCP across Rotherham
Lucy Smith – Head of Therapy, Chesterfield Royal Hospital
Joseph Henson – Clinical Lead First Contact Physiotherapy, Rotherham General Hospital
30th January 2019

## Slide 2: Headlines
How we got involved
Initial engagement with MSK Physiotherapy FCP
MSK FCP Pilot
Implementation of MSK Physiotherapy FCP pilot
Benefits and challenges
The positives of the service and the challenges we faced
Future of MSK FCP
Current and future plans for MSK Physiotherapy FCP

## Slide 3: Background
Rotherham NHS Foundation Trust
  Integrated acute & community
  Population of 260,000
  Diverse borough, densely populated, multi-ethnics in urban areas
  Aging population
Existing MSK service (MSK CATS & Physiotherapy)
15% increase in referrals (2016 to 2017)
Report submitted to Rotherham CCG suggesting MSK FCP
MSK FCP pilots:
  February 2017 – initial pilot, two practices, 8 weeks
  August 2017 – December 2017 – extended pilot, 10 practices, 4 APP

## Slide 4: August – December 2017 pilot
10 practices selected by Rotherham CCG
Capacity plan was identified
Clinician job plans developed
4 APP were recruited from the existing MSK physiotherapy team
Care Navigation model (West Wakefield) was adopted
Inclusion/ Exclusion criteria established
Data collection and patient feedback tools were developed

## Slide 5: August – December 2017 Pilot
Number of patients assessed / managed (NP – 1770, FU – 116)
Conditions
Chronicity
Outcomes of initial assessment/ follow up appointments
Investigations requested
Analysis of MSK and T+O referrals
Patient feedback
Notes: DNA rate – 5%
34% Lumbar, 16% shoulder, 16% knee
60% <3 months

## Slide 6: Pilot Results/ Success
Initial Assessment Outcomes
Appointment Outcome | Patients | Percentage
Provide education for self-management (no follow up) | 1092 | 62%
Referred to MSK Physiotherapy service | 458 | 26%
Referred back to GP | 63 | 4%
Inappropriate for MSK service | 34 | -
Appropriate but required further GP assistance | 29 | -
Other referral e.g. podiatry or community physiotherapy | 49 | 3%
Referred to MSK community assessment and treatment services | 40 | 2%
Follow up with the MSK Advanced Physiotherapy Practitioner | 35 | <2%
Referred to Trauma and Orthopaedic service | 14 | <1%
Incomplete assessment with no recorded outcome | 19 | 1%
Total | 1770 | -
Notes: GP assistance required - Approx 70% of cases was due to requiring pain relief

## Slide 7: Pilot Results/ Success
Follow up Appointment Outcomes
Appointment Outcome | Patients | Percentage
Referred to MSK Physiotherapy service | 48 | 41%
Continued self-management (no further appointment) | 44 | 38%
Referred to MSK community assessment and treatment services | 9 | 8%
Referred back to GP | 5 | 4%
Referred to Trauma and Orthopaedic service | 3 | 2%
Advised to wait for existing referral | 3 | 3%
Other referral e.g. podiatry or community physiotherapy | 3 | 3%
Follow up with the MSK Advanced Physiotherapy Practitioner | 1 | <1%
Total | 116 | -

## Slide 8: Pilot Results/ Success
Patient feedback
  30% response rate to satisfaction questionnaire
  99% likely to recommend the service
  999% happy to see APP instead of GP
  95% patients felt needs were met more efficiently
GP Feedback
  Positive / Supportive of project
  Reduced burden on GP appointments

## Slide 9: Detailed Analysis of Patient Outcomes
All 1770 patient Primary Care records were manually reviewed
68 patients referred back to GP by APP
313 patients accessed a further GP/ANP appointment
Appointment Outcome | Patients | Percentage
Prescribed pain relief | 157 | 41%
Prescribed pain relief and provided a fit note | 42 | 11%
Advised to wait for existing referral | 41 | 11%
Provided a fit note | 40 | 11%
Referred for MSK Physiotherapy | 34 | 9%
Referred to MSK CATs | 22 | 6%
Referred for an X-Ray | 17 | 4%
Referred to Trauma and Orthopaedics | 13 | 3%
Referred to other service | 11 | 3%
Did not attend appointment | 4 | 1%
Total | 381 | -

## Slide 10: Challenges
No significant reduction in referrals to MSK or T&O services
Lack of understanding of the MSK FCP role in practices
Lack of care navigation data
Capacity planning – baseline MSK data from GP practices
Reduction in MSK staff mid pilot
Prescribing

## Slide 11: Current Position of FCP in Rotherham
Results reported back to Rotherham CCG
Funding agreed for further provision and extension of service
12 months contract with Rotherham GP Federation to provide FCP across the whole borough within a Hub model
  5.4 WTE clinicians working across 10 Hubs
Recruitment in June 2018 including Clinical Lead
Full team established and model implemented September 2018

## Slide 12: Current Position of FCP in Rotherham
Patients care navigated to FCP via GP practices
Using Rotherham Out of Hours clinical systems
Established appropriate governance arrangements including escalation process
Training needs matched with ‘Musculoskeletal core capabilities framework for first point of contact practitioners’ (Skills for Health, 2018)
  Comprehensive induction
  MSc FCP module at UCLAN
  Established GP mentors

## Slide 13: Current Outcomes
Earlier access to assessment, intervention and signposting in the MSK pathway
Patient experience
  Very positive feedback via FFT
  Travel to the hubs
Amended CSP template to utilise for data collection
Initial signs show a reduction in MSK and Orthopaedic referrals from practices engaging with FCP

## Slide 14: Challenges
Care navigation
Clinical systems - EMIS/ SystmOne
Measuring impact on GP availability and pressures
  Number of GP appointments – affect on GP pressures
Impact on existing MSK service

## Slide 15: Opportunities
Potential saving of approximately 350 GP appointments per week
Reduction of MSK and T+O referrals
Continued positive patient experience and feedback
Professional development – challenging but rewarding environment

## Slide 16
ANY QUESTIONS?